## Product Backlog
PRODUCT BACKLOG
| ID | USER STORY | OWNER | PRIORITY | EFFORT in story points | STATUS | DEFINITION OF DONE | NOTES
|  |  |  | TOTAL | 114
| 1 | View home page | Product Owner | High | 3 | Completed | AuthControllerLoginTests unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members | Sprint1
| 2 | View admin dashboard | Product Owner | High | 3 | Completed | AuthControllerRegisterTests tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 3 | View customer dashboard | Product Owner | High | 3 | Completed | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 4 | View employee dashboard | Product Owner | High | 3 | Completed | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 5 | Register customer | Product Owner | High | 5 | Completed | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members | Sprint1
| 6 | User login | Product Owner | High | 5 | Completed | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members | Sprint1
| 7 | Add employee user | Product Owner | Medium | 3 | Completed | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 8 | Edit employee user | Product Owner | Medium | 3 | Todo | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 9 | Add working hours | Product Owner | Medium | 5 | Completed | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 10 | Edit working hours | Product Owner | Medium | 3 | Completed | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
- | 11 | View past bookings | Product Owner | Medium | 5 | Todo | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
- | 12 | View new bookings | Product Owner | Medium | 5 | Todo | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 13 | View weekly availability | Product Owner | Medium | 8 | Todo | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
- | 14 | View available service date/time | Product Owner | Medium | 8 | Todo | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
- | 15 | Book service | Product Owner | Medium | 8 | Todo | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 16 | View customer profile page | Product Owner | Medium | 5 | Todo | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 17 | Edit customer username | Product Owner | Low | 3 | Todo | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 18 | Edit customer password | Product Owner | Low | 3 | Todo | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 19 | Edit customer details | Product Owner | Low | 3 | Todo | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 20 | Cancel booking | Product Owner | Medium | 3 | Todo | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 21 | Get booking history | Product Owner | Medium | 5 | Todo | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 22 | View employee profile page | Product Owner | Medium | 5 | Todo | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 23 | Notification for Cancelled Booking | Product Owner | Low | 5 | Todo | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 24 | Edit Worker Profile | Product Owner | Low | 3 | Completed | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 25 | View A Worker Calendar | Product Owner | Medium | 3 | Todo | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 26 | Create A Business Owner Account | Product Owner | Medium | 3 | Completed | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
| 27 | Create A Business | Product Owner | Medium | 3 | Completed | Unit tests passed, acceptance tests passed, no known bugs in production, passed review by all team members
28
29
30
31
32
33
34
35
36
37
38
39
40

## Burndown Chart
Sprints | Days | SPs Completed | Ideal Burndown | PBIs Completed | Remaining Effort
Sprint 1 | 1 | 5 | 112.3714 | 5 | 109
| 2 | 0 | 110.7429 |  | 109
| 3 | 5 | 109.1143 | 6 | 104
| 4 | 0 | 107.4857 |  | 104
| 5 | 0 | 105.8571 |  | 104
| 6 | 6 | 104.2286 | 1,2 | 98
| 7 | 0 | 102.6 |  | 98
| 8 | 3 | 100.9714 | 3 | 95
| 9 | 0 | 99.3429 |  | 95
| 10 | 3 | 97.7143 | 4 | 92
| 11 | 0 | 96.0857 |  | 92
| 12 | 0 | 94.4571 |  | 92
| 13 | 0 | 92.8286 |  | 92
| 14 | 0 | 91.2 |  | 92
Sprint 2 | 15 |  | 89.5714
| 16 |  | 87.9429
| 17 |  | 86.3143
| 18 |  | 84.6857
| 19 |  | 83.0571
| 20 |  | 81.4286 |  |  | Total SPs | Days | Ideal Burnrate
| 21 |  | 79.8 |  |  | 114 | 70 | 1.6286
| 22 |  | 78.1714
| 23 |  | 76.5429
| 24 |  | 74.9143
| 25 |  | 73.2857
| 26 |  | 71.6571
| 27 |  | 70.0286
| 28 |  | 68.4
Sprint 3 | 29 |  | 66.7714
| 30 |  | 65.1429
| 31 |  | 63.5143
| 32 |  | 61.8857
| 33 |  | 60.2571
| 34 |  | 58.6286
| 35 |  | 57
| 36 |  | 55.3714
| 37 |  | 53.7429
| 38 |  | 52.1143
| 39 |  | 50.4857
| 40 |  | 48.8571
| 41 |  | 47.2286
| 42 |  | 45.6
Sprint 4 | 43 |  | 43.9714
| 44 |  | 42.3429
| 45 |  | 40.7143
| 46 |  | 39.0857
| 47 |  | 37.4571
| 48 |  | 35.8286
| 49 |  | 34.2
| 50 |  | 32.5714
| 51 |  | 30.9429
| 52 |  | 29.3143
| 53 |  | 27.6857
| 54 |  | 26.0571
| 55 |  | 24.4286
| 56 |  | 22.8
Sprint 5 | 57 |  | 21.1714
| 58 |  | 19.5429
| 59 |  | 17.9143
| 60 |  | 16.2857
| 61 |  | 14.6571
| 62 |  | 13.0286
| 63 |  | 11.4
| 64 |  | 9.7714
| 65 |  | 8.1429
| 66 |  | 6.5143
| 67 |  | 4.8857
| 68 |  | 3.2571
| 69 |  | 1.6286
| 70 |  | 0

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | View home page | #N/A | #N/A | #N/A | #N/A | #N/A
2 | View admin dashboard | #N/A | #N/A | #N/A | #N/A | #N/A
3 | View customer dashboard | #N/A | #N/A | #N/A | #N/A | #N/A
4 | View employee dashboard | #N/A | #N/A | #N/A | #N/A | #N/A
5 | Register customer | #N/A | #N/A | #N/A | #N/A | #N/A
6 | User login | #N/A | #N/A | #N/A | #N/A | #N/A
7 | Add employee user | #N/A | #N/A | #N/A | #N/A | #N/A
8 | Edit employee user | #N/A | #N/A | #N/A | #N/A | #N/A
9 | Add working hours | #N/A | #N/A | #N/A | #N/A | #N/A
10 | Edit working hours | #N/A | #N/A | #N/A | #N/A | #N/A
11 | View past bookings | #N/A | #N/A | #N/A | #N/A | #N/A
12 | View new bookings | #N/A | #N/A | #N/A | #N/A | #N/A
13 | View weekly availability | #N/A | #N/A | #N/A | #N/A | #N/A
14 | View available service date/time | #N/A | #N/A | #N/A | #N/A | #N/A
15 | Book service | #N/A | #N/A | #N/A | #N/A | #N/A
16 | View customer profile page | #N/A | #N/A | #N/A | #N/A | #N/A
17 | Edit customer username | #N/A | #N/A | #N/A | #N/A | #N/A
18 | Edit customer password | #N/A | #N/A | #N/A | #N/A | #N/A
19 | Edit customer details | #N/A | #N/A | #N/A | #N/A | #N/A
20 | Cancel booking | #N/A | #N/A | #N/A | #N/A | #N/A
21 | Get booking history | #N/A | #N/A | #N/A | #N/A | #N/A
22 | View employee profile page | #N/A | #N/A | #N/A | #N/A | #N/A
23 | Notification for Cancelled Booking | #N/A | #N/A | #N/A | #N/A | #N/A
24 | Edit Worker Profile | #N/A | #N/A | #N/A | #N/A | #N/A
25 | View A Worker Calendar | #N/A | #N/A | #N/A | #N/A | #N/A